## Slide 1: GOES Status
Elizabeth Kline, GOES-R Data Operations Manager (acting); PRO Team Lead (acting); GOES-R Product Quality Lead (permanent)
Steve Superczynski, Nick Carrasco, Sherrie Morris, Randy Race, Curtiss Burnett
Joint GRB-HRIT/EMWIN User Group Meeting - September 10, 2024

## Slide 2: Current GOES Constellation & GOES-19 Post-Launch Test (PLT) Phase
Current constellation diagram satellite roles are effective September 6, 2024
For a GOES-16/18 (East/West) anomaly, GOES-17 will be activated. If it is a warm season for the GOES-17 ABI loop heat pipe anomaly then GOES-14 will also be activated in series after GOES-17
  Field users leveraging smaller antennas (~5m) will not be able to simultaneously downlink GOES-17 GRB and GOES-14 GVAR due to interference because GRB will dominate the signal
Post-PLT, GOES-19 will replace GOES-16 at GOES-East
  Post-PLT destination of GOES-17 is 89.5W, GOES-16 is 104.7W, and GOES-14 is TBD (fuel & continuity with GeoXO in 2032 are among considerations)
GOES-17 checkout of spacecraft, instrument, and product generation will tentatively occur March 10-29, 2025, so GRB users may test their client-side data receipt and processing. GOES-16 checkout will not happen until 2026.
GOES-East
GOES-16
75.2°W
Standby
GOES-17
104.7°W
Co-Standby
GOES-14
108.2°W
GOES-West
GOES-18
137.0°W
Current
As of
9/9/2024
GOES-East
GOES-16
75.2°W
Standby
GOES-17
104.7°W
Co-Standby
GOES-14
108.2°W
GOES-West
GOES-18
137.0°W
GOES-19
PLT
(Post-Launch Test Phase)
Checkout
GOES-19
89.5°W
Ver: 9/9/24 E. Kline

## Slide 3: Current GOES Constellation & GOES-19 Post-Launch Test (PLT) Phase
GOES-East
GOES-16
75.2°W
Standby
GOES-17
104.7°W
Co-Standby
GOES-14
108.2°W
GOES-West
GOES-18
137.0°W
Current
As of
9/9/2024
GOES-East
GOES-16
75.2°W
Standby
GOES-17
104.7°W
Co-Standby
GOES-14
108.2°W
GOES-West
GOES-18
137.0°W
GOES-19
PLT
(Post-Launch Test Phase)
Checkout
GOES-19
89.5°W
Ver: 9/9/24 E. Kline
GOES-East
GOES-19
75.2°W
Standby
GOES-16
105°W
GOES-14
TBD
Checkout
GOES-17
89.5°W
GOES-West
GOES-18
137.0°W
GOES-19
T2O
(~4/4/25)
?
Notes: G19 moves to 75.2W, (2) G16 moves to 104.7W, (2) G17 moves to 89.5W, (4) G16 moves to 104.7W (probably); G14 moves to TBD
Two quick co-locations with 19&16 at ~75 and 16&17 at ~105.

## Slide 4: ABI Domains for Standby Operations
If GOES-East anomaly, then GOES-Storage to use default GOES-East MDS locations
If GOES-West anomaly, then GOES-Storage to use Pacific default MDS location and a modified Alaska MDS location (adjusted from 56N 150W)
Current
Scene centers | West Standby | East Standby
CONUS | 30°N, 137°W | 30°N, 95°W
Meso1 | 39°N, 120°W | 38.5°N, 75°W
Meso2 | 55°N, 140°W | 37°N, 86.5°W
East Standby (105W)
West Standby (105W)
Solid lines are Primary (West/East) view
Dashed lines are Standby (Storage) view
Ver: 9/9/24 R. Race

## Slide 5: GOES-East Transition Plan - Swap of GOES-16/19
GOES-East Operational Satellite
Legend:
Date (Based on 6/25/24 Launch) | GOES-16 |  | GOES-19 | 
 | Location | Activity | Location | Activity
6/25/24 – 7/24/24 | 75.2°W | GOES-East Operations |  | Launch and Orbit Raising
7/25/24 – 1/25/25 |  |  | 89.5°W | GOES-19 PLT and PLPT First public ABI Image (Vis & IR) @ 89.5°W GRB turned on and L1b added upon beta maturity
1/28/25 |  |  |  | GOES-19 Handover Readiness Review (HRR)
1/29/25 |  |  |  | GOES-19 Handover to NOAA
1/29/25 – 3/17/25 |  |  |  | GOES-19 Pre-Drift Product Checkout Avoid G17 Storage Checkout (3/10 – 3/29)
3/17/25 – 4/1/25 |  | GOES-16 “nudge“ to 75.5°W |  | GOES-19 Drift from 89.5°W to 75.2°W ~1 deg/day drift GRB Off for drift
4/1/25 | 75.5°W | GOES-16 in co-location configuration X-Band and S-Band downlink for colocation | 75.2°W | GOES-19 arrives at 75.2°W and instruments resume X-Band and L-Band downlink after drift for colocation
4/1/25 – 4/4/25 |  | GOES-16 in co-location configuration X-Band and S-Band downlink |  | GOES-19 Post-Drift Product Checkout at new location X-Band and L-Band downlink
4/3/25 |  |  |  | GOES-19 Operational Transition Readiness Review (OTRR)
4/4/25 |  | X-band downlink off and instruments shut down End GOES-16 GRB Broadcast |  | GOES-19 Declared operational GOES-East Begin GOES-19 GRB broadcast / nominal distribution SAR/DCS/HRIT/EMWIN services transitioned to GOES-19
4/4/25 |  | Begin GOES-16 drift to 105°W Drift using LTRs ~0.5 deg/day max drift rate |  | 
6/4/25 | 105°W | GOES-16 arrival at 105°W followed by storage mode GOES-17 to relocate to 89.5W (Storage Location) after GOES-16 arrival confirmed successful |  | 

## Slide 6: GOES-19 Transition to Operations
Ver: 9/6/24 E. Kline

## Slide 7
GOES-19 Post-Launch Milestones
Ver: 9/6/24 E. Kline
Complete
In Progress
Not Started/ECD
Not Started/ECD Changed
Component | Data Flow Initiated | First Light | First Public Image Release | Beta Certification | Provisional PS-PVR
ABI (L1b & CMI) | 8/20/2024 | 8/20/2024 (VNIR) 8/28/2024 (IR) | 9/18/2024 | 9/18/2024 | 1/3/2025
GLM | 8/20/2024 | 8/20/2024 | 10/3/2024 | 1/21/2025 | 3/27/2025
EXIS | 7/28/2024 | 9/13/2024 | 9/24/2024 | 10/18/2024 | 3/11/2025
GMAG | 7/22/2024 | N/A | 8/13/2024 | 10/9/2024 | 12/4/2024
SEISS | 8/22/2024 | 8/22/2024 | 9/4/2024 | 10/22/2024 | 11/29/2024 (SGPS)
 |  |  |  |  | 1/8/2025 (MPS-Hi)
 |  |  |  |  | 2/7/2025 (EHIS)
 |  |  |  |  | 2/11/2025 (MPS-Lo)
SUVI | 9/3/2024 | 9/24/2024 | 10/29/2024 | 11/4/2024 | 2/24/2025
CCOR | 8/30/2024 | 9/19/2024 | 10/22/2024 | 1/27/2025 | 2/24/2025

## Slide 8: GOES-R Ground Segment Product Portfolio
ABI L1b in GRB, PDA, CLASS, NODD
Radiances
GLM L2 in GRB, PDA, CLASS, NODD
Lightning: Events, Groups, Flashes
SEISS L1b in GRB, PDA, CLASS, NODD
Energetic Heavy Ions
Magnetospheric e-/p+: Low Energy
Magnetospheric e-/p+: High Energy
Solar & Galactic Protons
EXIS L1b in GRB, PDA, CLASS, NODD
Solar Flux: EUV
Solar Flux: X-ray Irradiance
SUVI L1b in GRB, PDA, CLASS, NODD
Solar EUV Imagery
GMAG L1b in GRB, PDA, CLASS, NODD
Geomagnetic Field
ABI L2+ Products in PDA, AWIPS, CLASS, NODD |  | ABI L2+ Products
Cloud and Moisture Imagery (CMI) and Sectorized CMI (KPP) |  | Fire/Hot Spot Characterization
Aerosol Detection (Smoke & Dust) * |  | Ice Age & Thickness *
Aerosol Optical Depth * |  | Ice Concentration & Extent *
Clear Sky Mask * |  | Ice Motion *
Cloud Cover Layers * |  | Land Surface Albedo *
Cloud Optical Depth * |  | Land Surface Reflectance *
Cloud Particle Size Distribution * |  | Land Surface Temperature *
Cloud Top Height * |  | Legacy Vertical Moisture Profile
Cloud Top Phase * |  | Legacy Vertical Temperature Profile
Cloud Top Pressure * |  | Rainfall Rate/QPE
Cloud Top Temperature * |  | Reflected S/W Radiation: TOA *
Derived Motion Winds * |  | Sea Surface Temperature
Derived Stability Indices |  | Snow Cover *
Downward S/W Radiation: Surface * |  | Total Precipitable Water
Legend: * Enterprise Algorithm
Some products also delivered via HRIT/EMWIN and GNC-A
noaasis.noaa.gov
GLM L2+ Products in AWIPS
Gridded Flash Extent Density, Minimum Flash Area, Total Optical Energy

## Slide 9: Science Products Training for 2024 and 2025
NWA Annual Meeting 2024, September 18, 2024
  Satellite User Engagement Workshop
EUMETSAT 2024, September 30, 2024; presentation on GEO international training: NOAA/NESDIS Training Experiences and Plans for Future International Satellite Applications Engagement
NOAA/WMO RA III Satellite Applications Training Workshop, March 2025
  Virtual with the Paraguay Space Agency (AEP), Directorate of Meteorology and Hydrology (DMH), NESDIS/IIAD and others
AMS Short Course before the Annual Meeting; January 12, 2025
Satellite Applications for Rainfall Rates and Flood Prediction
NOAA Satellite Conference, August 16-22, 2025 in La Jolla, CA
Ver: 8/26/24 S. Morris

## Slide 10: elizabeth.kline@noaa.gov stephen.superczynski@noaa.gov hector.n.carrasco@noaa.gov sherrie.morris@noaa.gov

## Slide 11: Soon Departing ABI L2+ Algorithms
Ver: 9/9/24 C. Burnett
Ice Motion
Product required mods to meet spec; AWIPS has capability to measure ice movement via manual measurement; Program Science decision to no pursue additional work to T2O
Path Forward
  ADR written to track, AART will manage process
  Turn off PG services on-prem (in-work, targeting post-DO.14 release)
  Halt implementation in L2 Cloud Migration (complete)
Rain Rate
Operational in NCCF (installed 6/12/24, PDA distribution 6/20/24), including an AWIPS-compatible GOES East/West version
Path Forward
  OSPO-managed decommissioning
  ADR written to track, AART will manage process
  Turn off of PG services on-prem
  Halt implementation in L2 Cloud Migration
Sea Surface Temperature
Enterprise Version planned will go live in NCCF in 2025
Path Forward: same as Rain Rate above